## Slide 1
Vision Empower
QUARTERLY FUNDER REPORT
Funder
Update
Generated 2 May 2026
Empowering Through Education
Tata Trusts · 1 Oct 2024 – 31 Dec 2024 · ₹25.0L
States: Karnataka, Tamil Nadu, Andhra Pradesh

## Slide 2
02
PROJECT OVERVIEW
About This Project
Vision Empower
2 / 9
This project trains teachers of visually impaired children across three southern states in modern inclusive education techniques including Braille, assistive technology, and classroom adaptation. Over 200 educators have been equipped with skills to create inclusive classrooms that give visually impaired children genuine access to quality education.
Beneficiaries: Visually impaired children · States: Karnataka, Tamil Nadu, Andhra Pradesh
₹25.0L
TOTAL GRANT
14
PROJECT DURATION (MONTHS)

## Slide 3
03
IMPACT
Key Impact at a Glance
Vision Empower
3 / 9
25%
DELIVERABLES
1 of 4 complete
77%
BUDGET USED
₹19.1L of ₹25.0L
97
TEACHERS REACHED
across all activities
209
STUDENTS REACHED
through project activities

## Slide 4
04
DELIVERABLES
Progress Against Plan
Vision Empower
4 / 9
1 of 4 deliverables complete
DELIVERABLE
TARGET
ACHIEVED
PROGRESS
STATUS
Teacher Training Workshops
120 teachers
87 teachers
73%
School Resource Kits Distributed
50 kits
50 kits
100%
Student Assessment Reports
500 students
312 students
62%
Peer Learning Networks Formed
10 networks
4 networks
40%

## Slide 5
05
ACTIVITIES
Field Activities & Reach
Vision Empower
5 / 9
Teacher Training Workshop — Bengaluru Batch 1
15 Oct 2024 · Karnataka
28 teachers · 5 schools
Teacher Training Workshop — Chennai Batch
2 Nov 2024 · Tamil Nadu
32 teachers · 7 schools
Resource Kit Distribution — Phase 1
10 Dec 2024 · Karnataka
120 students · 12 schools
Field Assessment Visit — AP Cluster
20 Jan 2025 · Andhra Pradesh
15 teachers · 89 students · 8 schools
Peer Learning Network Launch
5 Feb 2025 · Karnataka
22 teachers · 4 schools

## Slide 6
06
STORIES
Stories from the Field
Vision Empower
6 / 9
“
This training completely changed how I approach my classroom. My students with visual impairments are now participating fully in every lesson. The confidence I see in them every day makes everything worth it.
— Savitha K., Special Education Teacher, Bengaluru
Before this programme I felt lost teaching children who couldn't see the board. Now I have real tools and a community of teachers who understand the same challenges.
— Rajesh T., Primary Teacher, Chennai

## Slide 7
07
REACH
Geographic Coverage
Vision Empower
7 / 9
3
STATES COVERED
Karnataka
Tamil Nadu
Andhra Pradesh
97
TEACHERS
209
STUDENTS
36
SCHOOLS
5
ACTIVITIES
Karnataka: 120 students · 50 teachers Andhra Pradesh: 89 students · 15 teachers Tamil Nadu: 0 students · 32 teachers

## Slide 8
08
FINANCIALS
Budget & Utilisation
Vision Empower
8 / 9
₹25.0L
APPROVED BUDGET
₹19.1L
AMOUNT SPENT
₹5.8L
BALANCE REMAINING
77%
UTILISATION %
Budget breakdown by category
Personnel & Training Delivery
₹8.9L / ₹12.0L
74%
Materials & Resource Kits
₹6.0L / ₹6.0L
100%
Travel & Field Operations
₹2.8L / ₹4.0L
70%
Admin & Overhead
₹1.4L / ₹3.0L
48%

## Slide 9
WAY FORWARD
Challenges & Next Steps
Challenges
Field access was limited in several remote areas due to monsoon season, increasing travel costs and delaying two planned workshops. Teacher turnover at partner schools required additional onboarding sessions.
Next Steps
Expand programme to Hyderabad cluster in Q4. Recruit 20 additional facilitators. Complete remaining 33 teacher training slots by March 2025.
Vision Empower
9 / 9
Thank You
for your continued partnership
Empowering Through Education
Vision Empower Trust Enabling inclusive education for visually impaired children www.visionempower.in
Funded by Tata Trusts