## Slide 1
Vision Empower
QUARTERLY FUNDER REPORT
Funder
Update
Tata Trusts
Empowering Through Education
Period: 1 Oct 2024 – 31 Dec 2024 Grant: ₹25.0L States: Karnataka, Tamil Nadu, Andhra Pradesh
Generated 2 May 2026

## Slide 2
PROJECT OVERVIEW
At a Glance
Vision Empower
02 / 09
This project trains teachers of visually impaired children across three southern states in modern inclusive education techniques including Braille, assistive technology, and classroom adaptation.
₹25.0L
Total Grant Amount
14
Months
Project Duration

## Slide 3
KEY IMPACT
Key Impact at a Glance
Vision Empower
03 / 09
33%
Deliverables Complete
1 of 3
77%
Budget Utilisation
₹19.1L of ₹25.0L
75
Teachers Reached
across all activities
209
Students Reached
through project activities

## Slide 4
DELIVERABLES
Deliverables Progress
Vision Empower
04 / 09
Deliverable | Target | Achieved | % Complete | Status
Teacher Training Workshops | 120 teachers | 87 teachers | 73% | In Progress
School Resource Kits Distributed | 50 kits | 50 kits | 100% | Completed
Student Assessment Reports | 500 students | 312 students | 62% | In Progress

## Slide 5
FIELD ACTIVITIES
Field Activities
Vision Empower
05 / 09
Teacher Training — Bengaluru Batch
15 Oct 2024 · Karnataka
28 teachers · 5 schools
Teacher Training — Chennai Batch
2 Nov 2024 · Tamil Nadu
32 teachers · 7 schools
Resource Kit Distribution
10 Dec 2024 · Karnataka
120 students · 12 schools
Field Assessment Visit
20 Jan 2025 · Andhra Pradesh
15 teachers · 89 students · 8 schools

## Slide 6
STORIES FROM THE FIELD
Stories from the Field
Vision Empower
06 / 09
“
This training completely changed how I approach my classroom. The children are responding so much better now.
— Savitha K., Special Education Teacher, Bengaluru

## Slide 7
GEOGRAPHIC REACH
Geographic Reach
Vision Empower
07 / 09
3
States
covered
Karnataka
Tamil Nadu
Andhra Pradesh
Karnataka: 120 students · 28 teachers Andhra Pradesh: 89 students · 15 teachers Tamil Nadu: 0 students · 32 teachers

## Slide 8
FINANCIAL SUMMARY
Financial Summary
Vision Empower
08 / 09
₹25.0L
Approved Budget
₹19.1L
Amount Spent
₹5.8L
Balance Remaining
77%
Utilisation Rate
Budget Category | Approved (₹) | Spent (₹) | Balance (₹) | Utilised
Personnel & Training | 12,00,000 | 8,90,000 | 3,10,000 | 74%
Materials & Kits | 6,00,000 | 6,00,000 | 0 | 100%
Travel & Field Ops | 4,00,000 | 2,80,000 | 1,20,000 | 70%
Admin & Overhead | 3,00,000 | 1,45,000 | 1,55,000 | 48%

## Slide 9
Thank You
for your support of
Empowering Through Education
Vision Empower Trust Enabling inclusive education for visually impaired children www.visionempower.in
Funded by Tata Trusts
WAY FORWARD
Challenges & Next Steps
Challenges
Next Steps
Vision Empower
09 / 09